## Week of Oct 12-16 2026
Operational Highlights | Challenge / Issue / Risk | Action Plan
Roles, scope and rates (ERFWeb Phases 1, 2, 7): multi-role accounts with countersigned grants and an admin console; Level 2-maintained approval scope with routing at filing and versioned rate profiles; approval delegation for up to 90 days with "on behalf of" shown in the inbox and timeline. | Database scripts 006-013 must be applied by hand and in order on each environment. Migrating users.role and the old routes/rates tables is the riskiest step. Phase 7 delegation is pushed but not yet merged to master. | Open and merge the Phase 7 PR. Run scripts 006-013 on a test DB copy first and keep the old tables for rollback. Have the tester check role grants, routing coverage and delegation limits.
Approval, Finance and verification workflow (Phases 5, 6): approve, return, reject and Level 2 override with an approver inbox; Finance receipt queue up to Cleared for Payment; line verification requests and Level 2 queries. R47 printout now shows the L1/L2 approver names and signatures. | Separation-of-duties rules (no self-approval, no verifying a report you approved) need full end-to-end testing. The R47 signature branch is pushed but not yet merged. | Merge the R47 signature PR. Run a full report cycle (file, approve, Finance, verify, clear) with test users in each role before UAT.
SMS notifications and usability: Lasius SMS to the claimant and both signatories on filing, each approval, final approval, return and Finance follow-up, each verified live (202 accepted). Redesigned expense-line dialog with category defaults, plus a collapsible navigation pane. | SMS depends on the Lasius URL and API key being configured and on users having mobile numbers on file. Users with no number get no SMS. Gateway downtime is logged but does not block the workflow. | Confirm the Lasius settings on the deployment server. Fill in missing mobile numbers in user records. Watch the sms_deliveries table and audit counts after go-live.